## User Stories
# | User Story | AS A | I WANT TO | SO THAT | Story Points
1 | Visit Land Page | Generic User | Visit the Land Page of the Application | I can see contact, about and description of the application; in addition, I can navigate to sign up or login page | 3
2 | Sign Up | Generic User | Sign Up in the Application | I can register my profile on the Application | 8
3 | Sign In | Generic User | Authenticate against my profile | I can access my profile informations | 5
4 | Sign Out | Logged User | Sign Out from my profile | I can exit the Application | 1
5 | Visit Home Page | Logged User | Visit My Home Page | I can see the latest Advertisements in my location and I can have access to application features | 5
6 | Show User Profile | Logged User | Visit my Profile Page | I can see and edit my profile details, like name, email, birth date, gender, location; in addition I can upload a profile picture | 5
7 | Show User Advertisements | Logged User | Visit My Advertisement Page | I can see the ads I created earlier, edit them or and delete them if the related items have been sold | 3
8 | Insert Advertisement | Logged User | Insert an Advertisement specifying Category, Title, Description, Price and uploading a photo of the item | I can share the old item I want to sell with other users of the application. | 13
9 | Search Advertisements | Logged User | Search for an advertisement by Title, Location, Category | I can find the announcement relating to the items that are closest to my needs | 13
10 | Show Advertisement Detail | Logged User | Visit an Advertisement Detail Page | I can consult the details of the announcement and eventually contact the owner of the object via email | 5